EPM System — Complete User Stories

All Modules: Project & Task | Labour | Document | Procurement | Inventory | Resource | Budget | Risk | DPR | MVH Integration

| Epic | User Story ID | User Story | Role | Story Points | Acceptance Criteria | Technical Explanation |
| --- | --- | --- | --- | --- | --- | --- |
| Module I Project & Task Management | M1-1 | As a Project Manager, I want to create a new project so that I can initiate project planning and tracking. | Project Manager | 8 | 1. Multi-step form includes: Basic Info, Location, Timeline, and Budget sections. 2. Map picker for geo-location (Latitude/Longitude). 3. Project_ID auto-generated in format: Sequence-Country-SBU-Year. 4. All mandatory fields (Name, Country, SBU, Dates, Budget) must be filled. 5. End date must be greater than start date — validation error shown otherwise. 6. On successful save, system redirects to the Project Dashboard. 7. Duplicate Project_ID not allowed — uniqueness validated before insert. | UI: Multi-section form with yellow-black (Mount Meru) theme. Google Maps API integration for location picker. Backend: Auto-ID generation via sequence + country + SBU + year. Pre-insert uniqueness check. DB Table: Projects(Project_ID PK, Name, Country, SBU_Code, Year, Address, Latitude, Longitude, Baseline_Start, Baseline_End, Budget, Created_By, Created_On) |
| Module I Project & Task Management | M1-2 | As a Project Manager, I want to edit project details so that project information stays updated before execution begins. | Project Manager | 5 | 1. Editable form pre-populated with existing project data. 2. Project_ID field is disabled and non-editable. 3. Baseline dates show a lock icon after approval — not editable. 4. Edits allowed only when project status = 'Planned'. 5. Role check enforced — only PMs with edit permission can modify. 6. Audit columns (Updated_By, Updated_On) updated on every save. 7. If project is 'In Progress', editing is restricted and a warning is displayed. | UI: Prepopulated form with lock indicators on restricted fields. Backend: Status check before update; role-based permission gate. DB: UPDATE Projects SET ... WHERE Project_ID = ? AND Status = 'Planned'; audit columns auto-set. |
| Module I Project & Task Management | M1-3 | As a Project Manager, I want to define baseline start and end dates so that project planning is fixed and controlled. | Project Manager | 3 | 1. Date pickers for Baseline Start and Baseline End provided. 2. Baseline Start must be before Baseline End — validation enforced. 3. Once project is approved, baseline dates are locked and shown as read-only. 4. Admin override required to modify locked baseline dates. 5. Baseline dates stored separately from actual start/end dates. 6. System logs any baseline modification with user ID and timestamp. | UI: Calendar date pickers with visual lock icon post-approval. Backend: Separate columns for Baseline vs Actual dates; immutable after approval flag. DB: Baseline_Start_Date DATE, Baseline_End_Date DATE, Is_Baseline_Locked BOOLEAN |
| Module I Project & Task Management | M1-4 | As a Project Manager, I want to add sub-projects so that the project can be divided into logical components. | Project Manager | 5 | 1. 'Add Sub-Project' button available inside the project detail page. 2. Modal form contains: Sub-Project Name and Type (dropdown: RCC, Structural, PEB, Other). 3. Sub-Project automatically linked to the parent Project_ID. 4. Type must be selected from the predefined dropdown — free text not allowed. 5. Sub-Project list shown in a table under the project. 6. Sub-Project IDs auto-generated. | UI: Inline modal form triggered by 'Add Sub-Project' button. Backend: SubProject_ID generated; FK linked to Project_ID on insert. DB: SubProjects(SubProject_ID PK, Project_ID FK, Name, Type ENUM('RCC','Structural','PEB','Other')) |
| Module I Project & Task Management | M1-5 | As a Planning Engineer, I want to import tasks using MVH Excel so that I can quickly set up the project schedule. | Planning Engineer | 8 | 1. Upload button available on Task page with file type restricted to .xlsx/.xls. 2. Preview grid shows imported rows before final submission. 3. Editable cells in preview allow minor corrections before saving. 4. Validation errors shown inline per row (row number + error description). 5. Valid rows imported using a database transaction (all-or-nothing per batch). 6. Mandatory columns (Task Name, Start Date, End Date, Duration) must exist in the file. 7. Invalid rows are rejected and logged separately; valid rows are inserted. | UI: Upload button with progress indicator + editable preview grid. Backend: Excel parser (Apache POI / xlsx library) → schema validation → bulk insert via transaction. DB: Tasks(Task_ID PK, Project_ID FK, Parent_Task_ID, Name, Start_Date, End_Date, Duration, Created_By) |
| Module I Project & Task Management | M1-6 | As a System, I want to validate the uploaded Excel structure so that incorrect formats are rejected before import. | System | 5 | 1. System checks all required column headers exist in the uploaded file. 2. Data types validated per column (e.g., dates, numbers). 3. Error report table displayed showing: Row Number, Column, Error Description. 4. File with no valid rows is fully rejected with a clear error message. 5. Success vs. error count summary shown to user after validation. 6. Invalid rows logged to an error table in the database for audit purposes. | Backend: Schema validation layer checks column presence and data types before DB insert. DB: Import_Error_Log(Import_ID, Row_Number, Column_Name, Error_Description, Timestamp) UI: Error grid rendered post-upload with sortable row-level errors. |
| Module I Project & Task Management | M1-7 | As a Planning Engineer, I want to create task hierarchy up to 7 levels so that project planning is structured. | Planning Engineer | 8 | 1. Tasks can be nested with a maximum depth of 7 levels. 2. Tree view displayed with expand/collapse per node. 3. Visual indentation lines indicate hierarchy depth. 4. Parent-child relationship stored via Parent_Task_ID (self-referencing FK). 5. System prevents creation of an 8th level — validation error shown. 6. Summary tasks auto-aggregate duration/progress from children. | UI: Tree/outline view with toggle expand-collapse. Indentation per level. Backend: Recursive parent-child mapping with depth counter enforced at insert time. DB: Tasks table with Parent_Task_ID INT FK REFERENCES Tasks(Task_ID) |
| Module I Project & Task Management | M1-8 | As a Planning Engineer, I want to indent and outdent tasks so that the hierarchy can be adjusted dynamically. | Planning Engineer | 5 | 1. Indent button promotes a task one level deeper under the preceding sibling task. 2. Outdent button demotes a task one level up in the hierarchy. 3. Parent_Task_ID updated dynamically in the database on each action. 4. Hierarchy depth validated — task cannot be indented beyond level 7. 5. Task cannot be outdented beyond the root level (level 1). 6. Gantt chart and tree view refresh immediately after indent/outdent. | UI: Indent/Outdent toolbar buttons (similar to MS Project behavior). Backend: PATCH API updates Parent_Task_ID; depth recalculated recursively. DB: UPDATE Tasks SET Parent_Task_ID = ? WHERE Task_ID = ? |
| Module I Project & Task Management | M1-9 | As a Planning Engineer, I want to define task dependencies so that tasks are executed in the correct sequence. | Planning Engineer | 5 | 1. Predecessor dropdown available on each task with search functionality. 2. Supported dependency type: Finish-to-Start (default). 3. System prevents circular dependencies — validation error shown if circular link attempted. 4. Multiple predecessors allowed per task. 5. Dependency links visible on the Gantt chart as connecting arrows. 6. Predecessor_Task_ID stored per task. | UI: Multi-select predecessor search dropdown; dependency lines on Gantt. Backend: Graph traversal algorithm (DFS/BFS) to detect circular references before insert. DB: Task_Dependencies(Task_ID, Predecessor_Task_ID, Dependency_Type) |
| Module I Project & Task Management | M1-10 | As a System, I want to auto-adjust task schedules so that dependencies are respected when delays occur. | System | 8 | 1. When a task is delayed or its end date changes, all dependent tasks are auto-rescheduled. 2. Gantt chart visually updates to reflect cascaded date changes. 3. Critical path is recalculated after every reschedule. 4. Users receive notifications when their assigned tasks are auto-adjusted. 5. A log entry is created each time auto-adjustment occurs, recording old vs. new dates. 6. Manual override of auto-adjusted dates is allowed with a justification note. | Backend: Cascading scheduling algorithm triggered on task date change. Forward-pass CPM (Critical Path Method) used. DB: UPDATE Tasks SET Start_Date, End_Date WHERE Predecessor links exist. Notification: Event triggers pushed to affected users. |
| Module I Project & Task Management | M1-11 | As a Project Manager, I want to assign tasks to users so that accountability is clearly defined. | Project Manager | 3 | 1. User dropdown on task form, filtered by project role. 2. Only active users within the project are shown in the dropdown. 3. Assigned_To field stores the User_ID. 4. Notification sent to the assigned user upon task assignment. 5. Assigned user visible on task card and in Gantt chart. 6. Reassignment logs previous and new assignee with timestamp. | UI: Searchable user dropdown filtered by project membership and role. Backend: Assign User_ID to task; trigger notification event. DB: Tasks.Assigned_To INT FK REFERENCES Users(User_ID) |
| Module I Project & Task Management | M1-12 | As a User, I want to view tasks assigned to me so that I can focus on my responsibilities. | All Users | 3 | 1. Personal task dashboard with tabs: All, Today, Active, Delayed. 2. Tasks filtered by Assigned_To = current logged-in user. 3. Each task card shows: Task Name, Project, Due Date, Status, % Complete. 4. Delayed tasks highlighted in red. 5. Tasks sortable by due date, priority, and project. 6. Clicking a task opens detail view with full context. | UI: Dashboard with tabbed view. Color coding for status (green/yellow/red). Backend: SELECT * FROM Tasks WHERE Assigned_To = :current_user AND filters. DB: Tasks, joined with Projects for context display. |
| Module I Project & Task Management | M1-13 | As a Site Engineer, I want to update task progress so that real-time tracking is maintained. | Site Engineer | 5 | 1. Modal form available per task with fields: % Complete (0–100), Quantity, Remarks. 2. % Complete must be a number between 0 and 100. 3. System auto-captures Actual Start date on first progress update. 4. System auto-captures Actual End date when % Complete reaches 100. 5. Each update creates a new progress record (historical log maintained). 6. Progress summary visible on task row in real time. | UI: Modal form triggered from task row; inline update confirmation. Backend: INSERT into Task_Progress; auto-timestamp Actual_Start/End. DB: Task_Progress(Progress_ID PK, Task_ID FK, Percent_Complete, Quantity, Remarks, Updated_By, Updated_On) |
| Module I Project & Task Management | M1-14 | As a Site Engineer, I want to upload photos while updating progress so that work proof is maintained. | Site Engineer | 3 | 1. Drag-and-drop file upload area available within the progress update form. 2. Supported formats: JPG, PNG, PDF. 3. Maximum file size per upload: 10 MB. 4. Multiple photos can be uploaded per progress update. 5. Photos stored in cloud/local storage; file path saved in DB. 6. Uploaded photos viewable from the task detail page in a gallery view. | UI: Drag-and-drop zone; thumbnail preview after upload. Backend: Multipart form upload; file saved to cloud storage (S3/local); path stored. DB: Task_Media(Media_ID PK, Task_ID FK, File_Path, Uploaded_By, Uploaded_On) |
| Module I Project & Task Management | M1-15 | As a System, I want to auto-capture actual start and end dates so that manual errors are eliminated. | System | 3 | 1. Actual Start Date auto-set when first progress entry is submitted for a task. 2. Actual End Date auto-set when % Complete = 100. 3. These dates cannot be manually edited by the user. 4. Admin can override with justification note. 5. Timestamps stored in UTC and displayed in local timezone. 6. Audit log records each auto-capture event. | Backend: Trigger on Task_Progress insert — check if Actual_Start is NULL; if yes, set to CURRENT_TIMESTAMP. For completion: IF percent = 100, SET Actual_End = CURRENT_TIMESTAMP. DB: Tasks(Actual_Start DATETIME, Actual_End DATETIME) |
| Module I Project & Task Management | M1-16 | As a Site Engineer, I want to log delays so that issues impacting the project are recorded. | Site Engineer | 5 | 1. Delay form accessible from any task row. 2. Form fields: Delay Type (dropdown: Weather, Material, Labour, Equipment, Client, Other), Delay Hours (numeric), Description (text area). 3. Delay Type must be selected from predefined dropdown. 4. Delay Hours must be a positive number. 5. Each delay record linked to the specific Task_ID. 6. Logged delays reflected in task status as 'Delayed'. 7. Delay summary visible in dashboard. | UI: Delay form as inline modal with type dropdown and text area. Backend: INSERT into Task_Delay; update task status flag. DB: Task_Delay(Delay_ID PK, Task_ID FK, Type ENUM, Hours DECIMAL, Description TEXT, Logged_By, Logged_On) |
| Module I Project & Task Management | M1-17 | As a Manager, I want to view delayed tasks so that corrective action can be taken immediately. | Manager | 3 | 1. Delayed tasks highlighted in red in the task list and Gantt chart. 2. Filter option available to show only delayed tasks. 3. Delay details (type, hours, description) accessible per task. 4. Dashboard widget shows count of delayed tasks per project. 5. Email/in-app notification sent to PM when a task is marked delayed. 6. Export option available for delayed task report. | UI: Red highlight + filter toggle in task list. Dashboard KPI widget. Backend: Query Tasks WHERE Due_Date < TODAY AND Percent_Complete < 100. DB: JOIN with Task_Delay for delay context; indexed on Status and Due_Date. |
| Module I Project & Task Management | M1-18 | As a User, I want to search tasks so that I can quickly locate specific tasks. | All Users | 2 | 1. Global search bar present at top of task pages. 2. Search queries Task Name, Task ID, and Assigned User. 3. Results displayed in real-time as user types (debounced). 4. Search works across all projects the user has access to. 5. Clicking a search result opens the task detail page. 6. No results returns a clear 'No tasks found' message. | UI: Global search bar with live results dropdown. Backend: Full-text search query on Tasks table (indexed columns: Name, Task_ID). DB: CREATE FULLTEXT INDEX on Tasks(Name); query with MATCH AGAINST. |
| Module I Project & Task Management | M1-19 | As a User, I want to filter tasks so that I can narrow down relevant data. | All Users | 2 | 1. Sidebar filter panel available on task list view. 2. Filter options: Status, Date Range, Assigned User, Priority, Project. 3. Multiple filters can be applied simultaneously. 4. Applied filters persist within the session. 5. 'Clear All Filters' button resets to default view. 6. Filter results update the task list and Gantt chart in real time. | UI: Sidebar filter panel with multi-select dropdowns and date pickers. Backend: Dynamic query builder assembles WHERE clauses from active filters. DB: Parameterized queries with indexed filter columns. |
| Module I Project & Task Management | M1-20 | As a Project Manager, I want to perform bulk updates on tasks so that time is saved. | Project Manager | 5 | 1. Checkbox column in task list allows multi-task selection. 2. Bulk action menu appears when one or more tasks are selected. 3. Available bulk actions: Update Status, Reassign User, Change Due Date. 4. Confirmation dialog shown before bulk update is applied. 5. All selected tasks updated in a single API call. 6. Audit log entry created for each task modified in bulk. | UI: Checkbox column + floating bulk action toolbar. Backend: Batch update API endpoint accepting array of Task_IDs + update payload. DB: UPDATE Tasks SET field = value WHERE Task_ID IN (...); wrapped in transaction. |
| Module I Project & Task Management | M1-21 | As a Project Manager, I want to mark tasks as milestones so that key deliverables are visually tracked and reported. | Project Manager | 2 | 1. Toggle flag button available on each task to mark/unmark as milestone. 2. Milestone tasks shown with a distinct diamond symbol on the Gantt chart. 3. Milestones have zero duration by definition. 4. Milestone column in task list shows Yes/No status. 5. Milestone report filterable separately from regular tasks. 6. Missed milestones trigger an alert notification to the PM. | UI: Toggle switch on task row; diamond icon in Gantt. Backend: Update Is_Milestone boolean flag. DB: Tasks.Is_Milestone BOOLEAN DEFAULT FALSE; indexed for milestone-specific queries. |
| Module I Project & Task Management | M1-22 | As a User, I want to view a Gantt chart so that the project schedule is visualized clearly. | All Users | 8 | 1. Gantt chart displays all tasks on a horizontal timeline. 2. Each task bar shows start date, end date, and % completion fill. 3. Dependency arrows rendered between linked tasks. 4. Milestones shown as diamonds. 5. Critical path highlighted in red. 6. Timeline zoom: day, week, month, quarter views available. 7. Gantt chart scrollable horizontally and vertically. | UI: Interactive Gantt chart using a library (e.g., DHTMLX Gantt or Frappe Gantt). Backend: Chart data API returns tasks with dependencies, baseline, and actual dates. DB: JOIN Tasks with Task_Dependencies for arrow rendering. |
| Module I Project & Task Management | M1-23 | As a System, I want to calculate the critical path so that the longest chain of dependent tasks is identified. | System | 8 | 1. Critical path calculated using CPM (Critical Path Method) algorithm. 2. Tasks on the critical path are highlighted in red on the Gantt chart. 3. Critical path recalculated whenever task dates or dependencies change. 4. Float (slack) time displayed per task. 5. Critical path tasks cannot be delayed without impacting project end date. 6. Critical path report exportable. | Backend: Forward and backward pass CPM algorithm executed on task dependency graph. Gantt: Tasks with Float = 0 highlighted red. DB: Computed Float stored per task; recomputed on schedule change. |
| Module I Project & Task Management | M1-24 | As a User, I want to receive notifications so that I am informed of task assignments, updates, and delays. | All Users | 3 | 1. In-app notification bell icon shows unread count. 2. Notifications triggered for: task assignment, task delay, milestone missed, progress updated. 3. Email notifications sent for high-priority events. 4. Notification includes: event type, task name, project name, timestamp. 5. User can mark notifications as read individually or all at once. 6. Notification history retained for 30 days. | Backend: Event-driven notification service. Queue-based (e.g., Redis/RabbitMQ) for async delivery. DB: Notifications(Notif_ID, User_ID, Type, Message, Is_Read, Created_On) Email: SMTP or SendGrid integration for email dispatch. |
| Module I Project & Task Management | M1-25 | As a User, I want role-based access control so that I can only access data and actions relevant to my role. | All Users | 5 | 1. User roles defined: Admin, Project Manager, Planning Engineer, Site Engineer, Viewer. 2. Each role has specific permissions: Create, Read, Update, Delete per module. 3. Menu items and buttons hidden/disabled based on role. 4. API endpoints enforce role checks server-side. 5. Unauthorized access attempts return HTTP 403 and are logged. 6. Role assignment managed via Admin panel. | Backend: RBAC middleware checks user role on every API request. DB: Users(Role), Role_Permissions(Role, Module, Can_Create, Can_Read, Can_Update, Can_Delete). UI: Conditional rendering of buttons and menu items based on role flags. |
| Module I Project & Task Management | M1-26 | As a Project Manager, I want to export tasks to Excel so that reporting and sharing is easy. | Project Manager | 3 | 1. 'Export' button available on task list view. 2. Export includes all currently visible/filtered tasks. 3. File format: .xlsx with proper column headers. 4. Export includes: Task ID, Name, Start Date, End Date, Status, Assigned User, % Complete. 5. Large exports (>1000 rows) processed asynchronously with a download link sent. 6. Exported file formatted with bold headers and alternating row colors. | UI: Export button triggers file download or async job. Backend: Server-side Excel generation using Apache POI / xlsx library. Response: Streamed file download or async job with download URL. |
| Module I Project & Task Management | M1-27 | As a System, I want to maintain audit logs so that all task changes are traceable for compliance and debugging. | System | 3 | 1. Every create, update, and delete action on a task is logged. 2. Log entry includes: User_ID, Action Type, Table Name, Record_ID, Old Value, New Value, Timestamp. 3. Audit logs are read-only — not editable by any user. 4. Admin can view audit logs via a dedicated panel. 5. Logs retained for a minimum of 1 year. 6. Log entries filterable by user, date range, and action type. | Backend: AuditLog interceptor/middleware records changes before/after UPDATE or DELETE. DB: Audit_Log(Log_ID PK, User_ID, Action, Table_Name, Record_ID, Old_Value JSON, New_Value JSON, Timestamp) |
| Module I Project & Task Management | M1-28 | As a Project Manager, I want to clone a task so that repetitive tasks can be reused without re-entering data. | Project Manager | 3 | 1. 'Clone Task' option available from task context menu. 2. Cloned task pre-populated with all fields from source task. 3. New Task_ID generated automatically for the clone. 4. Clone created as a sibling of the original (same parent). 5. Dependencies NOT cloned by default (configurable option). 6. User can edit the cloned task before saving. | Backend: Deep copy of task record; new Task_ID generated; dependencies optionally excluded. DB: INSERT INTO Tasks (SELECT all fields FROM Tasks WHERE Task_ID = ?) with new ID. |
| Module I Project & Task Management | M1-29 | As a System, I want to log all API requests and responses so that debugging and monitoring are possible. | System | 3 | 1. Every API call logged with: endpoint, method, user, request payload, response status, latency. 2. Failed API calls (4xx, 5xx) logged with full error context. 3. API logs stored separately from application logs. 4. Log viewer available to system admin. 5. Logs support filtering by endpoint, status code, user, and date. 6. Alerts triggered when error rate exceeds threshold. | Backend: API gateway or middleware logs every request/response pair. DB or Log Storage: API_Logs(Log_ID, Endpoint, Method, User_ID, Status_Code, Latency_ms, Timestamp) Monitoring: Integration with ELK stack or similar logging tool. |
| Module I Project & Task Management | M1-30 | As a User, I want to add comments to tasks so that team collaboration and communication are improved. | All Users | 3 | 1. Comment section available at the bottom of each task detail page. 2. Comment field accepts plain text; supports @mentions for user tagging. 3. Mentioned users receive notifications. 4. Comments shown in chronological order with username and timestamp. 5. Comment author can edit or delete their own comments. 6. Comment history retained indefinitely. | UI: Threaded comment section with @mention autocomplete. Backend: INSERT on submit; push notification to mentioned users. DB: Task_Comments(Comment_ID PK, Task_ID FK, User_ID FK, Content TEXT, Created_On, Updated_On) |
| Module II Labour Management | M2-1 | As a Site Engineer, I want to record daily labour attendance so that workforce productivity is tracked per task. | Site Engineer | 5 | 1. Labour entry form displayed in table format with trade rows (Mason, Welder, Electrician, Carpenter, Helper, etc.). 2. For each trade: Planned Count and Actual Count input fields. 3. Entry linked to a specific Task_ID and Date. 4. Values must be numeric — non-numeric input shows validation error. 5. Planned count editable; actual count entered at end of day. 6. Duplicate entry for same Task_ID + Trade + Date not allowed. | UI: Table-format entry form with trade rows and numeric inputs. Backend: INSERT with unique constraint on (Task_ID, Trade, Date). DB: Labour_Attendance(Attendance_ID PK, Task_ID FK, Trade, Planned INT, Actual INT, Date DATE, Created_By) |
| Module II Labour Management | M2-2 | As a Project Manager, I want to compare planned vs actual labour so that workforce efficiency can be measured. | Project Manager | 5 | 1. Bar chart dashboard shows planned vs actual labour per day and per task. 2. Variance column (Actual - Planned) shown in a data table. 3. Negative variance (under-deployment) highlighted in red. 4. Filters available: by date range, trade type, sub-project. 5. Summary KPIs: Total Planned, Total Actual, Overall Variance. 6. Data exportable to Excel. | UI: Chart.js or similar bar chart with grouped bars per trade. Backend: Aggregation query: SELECT Trade, SUM(Planned), SUM(Actual), (SUM(Actual)-SUM(Planned)) AS Variance FROM Labour_Attendance GROUP BY Trade. DB: Indexed on Task_ID, Date. |
| Module II Labour Management | M2-3 | As a User, I want to categorize labour by trade so that reporting is structured and filterable. | All Users | 2 | 1. Labour type dropdown includes predefined trades: Mason, Welder, Electrician, Carpenter, Helper, Supervisor, and Others. 2. 'Others' option allows free-text description. 3. Trade list managed by admin from a master settings page. 4. Reports filterable by trade category. 5. Trade type stored as an enum or FK to Labour_Type master table. | Backend: Enum mapping or master table for Labour_Type. DB: Labour_Type(Type_ID PK, Name VARCHAR) as master; Labour_Attendance.Trade FK to Labour_Type. UI: Dropdown with search functionality. |
| Module II Labour Management | M2-4 | As a Manager, I want a labour dashboard so that daily and weekly workforce insights are visible at a glance. | Manager | 5 | 1. Dashboard shows daily and weekly labour deployment charts. 2. Widgets include: Today's Labour Count, Weekly Trend Chart, Trade-wise Distribution (pie chart). 3. Site-wise and project-wise filter available. 4. Dashboard auto-refreshes every 30 minutes. 5. Drill-down available from chart to underlying task-level data. 6. Exportable as PDF report. | UI: Card-based dashboard with Chart.js charts (bar, pie, line). Backend: Aggregation API endpoints per widget. DB: Aggregated queries on Labour_Attendance grouped by Date, Trade, Project. |
| Module II Labour Management | M2-5 | As a System, I want to store daily attendance records so that historical labour data is available for reporting. | System | 3 | 1. Every labour entry saved with date stamp, task reference, and user who entered it. 2. Historical records never deleted — soft delete only. 3. Attendance data queryable by date range, project, and trade. 4. Data accessible from DPR and labour reports. 5. Retention policy: minimum 3 years. | DB: Labour_Attendance table with Date, Task_ID, Trade, Planned, Actual, Created_By, Is_Active. Backend: No hard deletes; Is_Active = FALSE for soft delete. Indexes on Date, Task_ID for fast historical queries. |
| Module II Labour Management | M2-6 | As a Manager, I want trade-wise productivity metrics so that efficiency of each skill category is measured. | Manager | 5 | 1. Table showing productivity ratio per trade: Actual/Planned × 100%. 2. Bar chart visualizing trade-wise efficiency. 3. Trades below 80% efficiency highlighted in red. 4. Date range filter available. 5. Exportable report for weekly review meetings. | Backend: Compute productivity = SUM(Actual)/SUM(Planned)*100 per Trade. UI: Bar chart + sortable table with conditional formatting. DB: Aggregation on Labour_Attendance GROUP BY Trade. |
| Module II Labour Management | M2-7 | As a System, I want to map labour costs to tasks so that budgeting integration is possible. | System | 5 | 1. Each trade has a configured daily rate in the system. 2. Labour cost per task calculated as: Actual Count × Daily Rate × Days. 3. Labour cost feeds into the Budget module under the 'Labour' budget category. 4. Cost visible in task detail and in budget dashboard. 5. Daily rates configurable by admin. | Backend: Labour_Cost = Actual_Count × Rate × Days computed on demand or stored. DB: Labour_Rates(Trade, Daily_Rate, Effective_Date); Labour_Attendance joined with rates for cost calc. Integration: Labour cost API consumed by Budget module. |
| Module II Labour Management | M2-8 | As a User, I want a mobile-friendly UI so that site engineers can input labour data easily from the field. | Site Engineer | 5 | 1. UI fully responsive — works on 360px–1920px screen widths. 2. Labour entry form optimized for touch input (large tap targets). 3. Dropdown selectors use native mobile controls. 4. Form auto-saves draft on mobile to prevent data loss. 5. Works offline (PWA cache) and syncs when reconnected. 6. Form submission confirmed with visual feedback (toast message). | UI: Responsive CSS grid/flexbox; PWA with service worker for offline capability. Backend: Sync endpoint for queued offline submissions. DB: Pending_Sync queue table for offline entries. |
| Module II Labour Management | M2-9 | As a Supervisor, I want to approve labour entries so that data accuracy and accountability are ensured. | Supervisor | 5 | 1. Labour entries submitted by site engineer go into 'Pending Approval' state. 2. Supervisor sees a list of pending entries per date/project. 3. Approve or Reject action available per entry. 4. Rejection requires a mandatory remarks field. 5. Approved entries are locked and cannot be edited. 6. Approval action logged with approver User_ID and timestamp. | UI: Approval queue list with Approve/Reject buttons and remarks modal. Backend: Status transition: Pending → Approved/Rejected; lock record on approval. DB: Labour_Attendance.Status ENUM('Pending','Approved','Rejected'), Approved_By, Approved_On. |
| Module II Labour Management | M2-10 | As a System, I want labour data to automatically feed into the DPR so that daily reports are generated without manual effort. | System | 5 | 1. DPR generation pulls latest approved labour data for the day. 2. Labour section in DPR shows: trade-wise planned vs actual deployment. 3. If labour data is not yet approved by DPR generation time, pending data shown with a flag. 4. Data pulled in real time — no manual copy required. 5. Labour data in DPR exportable with full task context. | Backend: DPR generation service queries Labour_Attendance WHERE Date = TODAY AND Status = 'Approved'. Integration: Labour module exposes API endpoint consumed by DPR service. DB: JOIN Labour_Attendance with Tasks, Projects for context. |
| Module III Document Management | M3-1 | As a Project Manager, I want to upload documents so that all project files are centrally stored and accessible by the team. | Project Manager | 5 | 1. Upload form includes: Project (dropdown), Document Type, Folder Level 1–3, Document ID, File upload. 2. Drag & drop upload supported alongside click-to-browse. 3. Supported file types: PDF, DOCX, XLSX, DWG, JPG, PNG. 4. Maximum file size: 50 MB. 5. Document ID must be unique and max 20 characters. 6. File stored in cloud/local storage; metadata saved in database. 7. Duplicate Document_ID rejected with validation error. | UI: Drag-and-drop upload zone with file type and size validation. Backend: File stored in S3 or local storage; metadata inserted to Documents table. DB: Documents(Document_ID PK, Project_ID FK, Type, Folder1, Folder2, Folder3, File_Path, Uploaded_By, Uploaded_On) |
| Module III Document Management | M3-2 | As a User, I want to navigate documents through a folder hierarchy so that I can easily locate and organize files. | All Users | 3 | 1. Three-level folder hierarchy displayed as a tree structure. 2. Tree nodes expandable and collapsible. 3. Breadcrumb navigation shows current location path. 4. Clicking a folder shows documents within it. 5. Folder path displayed as: Level1 > Level2 > Level3. 6. Empty folders display a 'No documents found' message. | UI: Recursive tree component with expand/collapse. Breadcrumb bar above document list. Backend: Fetch documents WHERE Folder1 = ? AND Folder2 = ? AND Folder3 = ?. DB: Documents.Folder1, Folder2, Folder3 VARCHAR columns. |
| Module III Document Management | M3-3 | As a User, I want to filter documents by type so that I can quickly find relevant files without browsing all folders. | All Users | 2 | 1. Dropdown filter available: RFQ, BOM, QC Docs, Drawings, Contracts, Site Photos, Other. 2. Multiple document types selectable simultaneously. 3. Filter applied instantly — document list updates without page reload. 4. Active filters shown as removable tags above the document list. 5. 'Clear Filters' resets to full list. | UI: Multi-select dropdown filter with active filter tags. Backend: Dynamic query with WHERE Type IN (?) clause. DB: Documents.Type indexed for fast filtering. |
| Module III Document Management | M3-4 | As a Project Manager, I want to control access to documents so that only authorized users can edit or view sensitive files. | Project Manager | 5 | 1. Lock icon displayed on restricted documents. 2. Role labels shown on document (e.g., 'PM Only', 'All Team'). 3. Access levels: View Only, Download, Upload, Edit, Delete — per role. 4. RBAC enforced both in UI (hide buttons) and API (server-side check). 5. Unauthorized access attempt logs event and returns 403. 6. Access rules configurable per project from admin panel. | Backend: RBAC middleware checks Document_Access(Role, Permission) before serving file. DB: Document_Access(Role VARCHAR, Document_Type, Can_View, Can_Download, Can_Upload, Can_Delete BOOLEAN) UI: Conditional rendering of action buttons based on role. |
| Module III Document Management | M3-5 | As a Planning Engineer, I want to upload drawings so that technical designs are stored, versioned, and shared with the team. | Planning Engineer | 5 | 1. Drawing upload form includes: Drawing Name, Category (Structural/Architectural/MEP), Revision Number, Sub-project. 2. File types supported: DWG, PDF, DXF. 3. Drawing metadata saved along with file path. 4. Initial upload creates Revision v1. 5. Drawing appears in Drawing Register with category tag. 6. Uploaded drawing notifies relevant team members. | UI: Drawing upload form with category and revision fields. Backend: Save drawing metadata + file; set initial Revision = 1. DB: Drawings(Drawing_ID PK, Name, Category, Revision INT, Sub_Project_ID FK, File_Path, Uploaded_By, Uploaded_On) |
| Module III Document Management | M3-6 | As a System, I want to manage drawing versions so that revision history is maintained and previous versions are accessible. | System | 5 | 1. Each new upload of an existing drawing auto-increments revision number (v1, v2, v3…). 2. Version badge displayed on drawing row. 3. All previous versions accessible from version history panel. 4. Previous versions downloadable but marked as 'Superseded'. 5. Revision notes required when uploading a new version. | Backend: On upload, check existing Drawing_ID; if exists, increment MAX(Revision) + 1. DB: Drawing_Versions(Version_ID PK, Drawing_ID FK, Revision INT, File_Path, Notes, Uploaded_By, Uploaded_On) UI: Version history drawer/modal per drawing. |
| Module III Document Management | M3-7 | As a User, I want to view only the latest drawing revision so that outdated versions are not accidentally used. | All Users | 2 | 1. Default drawing list view shows only the latest revision per drawing. 2. Latest revision tagged with a 'Latest Version' badge. 3. Older versions accessible via 'View All Versions' toggle. 4. Download button on default view downloads latest version only. 5. Superseded versions display a warning banner when opened. | Backend: Fetch drawings WHERE Revision = MAX(Revision) per Drawing_ID. UI: 'Latest Version' badge; 'View All Versions' toggle. DB: Drawing_Versions with indexed Revision; latest version fetched via subquery. |
| Module III Document Management | M3-8 | As a Planning Engineer, I want to track drawing lifecycle status so that approval flow is maintained and team knows current state. | Planning Engineer | 3 | 1. Drawing status workflow: Draft → Released → Revised → Obsolete. 2. Status transition buttons shown based on current state and user role. 3. Status badge displayed on drawing row. 4. Only Planning Engineer or PM can transition status. 5. Status change logged with user and timestamp. 6. Email notification sent to team on status change. | Backend: State machine logic validating allowed transitions per role. DB: Drawings.Status ENUM('Draft','Released','Revised','Obsolete'), Status_Changed_By, Status_Changed_On UI: Status badge with color coding (grey/green/yellow/red). |
| Module III Document Management | M3-9 | As a User, I want to search documents so that I can quickly locate files by name, ID, or type. | All Users | 2 | 1. Global search bar available on document pages. 2. Search across: Document_ID, Document Name, Type, Folder. 3. Results shown in real time as user types. 4. Search results include file type icon, document name, upload date, project name. 5. Click on result opens document detail page. 6. No results shown with 'No documents found' message. | Backend: Full-text search on Documents(Document_ID, Name); filter by Type and Project_ID. DB: FULLTEXT INDEX on Documents(Name, Document_ID). UI: Live search with debounced API calls. |
| Module III Document Management | M3-10 | As a User, I want to download documents so that I can use or share them offline. | All Users | 2 | 1. Download button available on each document row and detail page. 2. File retrieved securely from storage (pre-signed URL for cloud or streamed from server). 3. Download action logged with user ID and timestamp. 4. Role-based permission enforced — only authorized users can download. 5. Large files show a progress bar during download. | Backend: Generate pre-signed S3 URL or stream file response. DB: Download_Log(Document_ID, User_ID, Downloaded_On) for audit. Permission: Check Document_Access before serving file. |
| Module III Document Management | M3-11 | As a System, I want to maintain document audit logs so that all changes are traceable for compliance purposes. | System | 3 | 1. Every create, update, delete, and download action on a document is logged. 2. Log entry includes: User_ID, Action, Document_ID, Old/New values, Timestamp. 3. Audit logs read-only — not editable. 4. Admin can view and filter audit logs by user, document, or action type. 5. Retained for minimum 2 years. | Backend: Audit interceptor on all Document API endpoints. DB: Document_Audit_Log(Log_ID PK, User_ID, Action ENUM('Create','Update','Delete','Download'), Document_ID, Details JSON, Timestamp) |
| Module III Document Management | M3-12 | As a Project Manager, I want to create change requests so that any project modifications are formally tracked and documented. | Project Manager | 5 | 1. Change Request form includes: Title, Description (rich text), Impact Area, Attachment, Sub-project linkage. 2. CR_ID auto-generated. 3. Form submission creates CR in 'Discussion' status. 4. CR linked to specific project and optional sub-project. 5. All stakeholders notified on CR creation. 6. CR list paginated and filterable by status and date. | UI: CR creation form with attachment upload and rich text description. Backend: INSERT with auto-generated CR_ID; trigger notification. DB: Change_Request(CR_ID PK, Project_ID FK, Title, Description TEXT, Status, Sub_Project_ID, Created_By, Created_On) |
| Module III Document Management | M3-13 | As a System, I want to manage the change request approval workflow so that each stage is tracked and recorded. | System | 8 | 1. CR workflow stages: Discussion → Review → Costing → Approval → Implementation → Closed. 2. Status tracker (stepper UI) displays current stage. 3. Each stage transition requires authorization from the assigned role. 4. Stage transition logged with user, remarks, and timestamp. 5. Notifications triggered at each stage change. 6. Rejection at any stage returns CR to Discussion with remarks. | Backend: Workflow state machine; role-based stage transitions enforced. DB: CR_Status_Log(Log_ID, CR_ID, Stage, Changed_By, Remarks, Changed_On) UI: Horizontal stepper showing current and completed stages. |
| Module III Document Management | M3-14 | As a Manager, I want a document dashboard so that I can monitor document distribution and status across projects. | Manager | 3 | 1. Dashboard shows pie chart of documents by category. 2. KPI cards: Total Documents, Pending Reviews, Recent Uploads. 3. Bar chart for upload activity over time. 4. Filter by project and date range. 5. Drill-down from chart to document list. 6. Exportable as PDF report. | UI: Pie and bar charts using Chart.js; KPI card components. Backend: Aggregation queries per widget. DB: GROUP BY Type, Status, DATE(Uploaded_On) on Documents table. |
| Module III Document Management | M3-15 | As a User, I want to bulk upload multiple documents so that initial project setup is completed efficiently. | All Users | 5 | 1. Multi-file upload supported (select multiple files at once or drag multiple). 2. Each file shows individual progress bar during upload. 3. Common metadata (Project, Document Type, Folder) applied to all files in the batch. 4. Individual metadata override per file supported. 5. Failed uploads shown with retry option. 6. Successful batch upload shown with count summary. | UI: Multi-file drop zone with individual progress indicators. Backend: Parallel file uploads; batch metadata insert. DB: Bulk INSERT into Documents with shared and individual metadata. |
| Module IV Procurement Tracker | M4-1 | As a Site Engineer, I want to create a Material Request so that the procurement process is formally initiated. | Site Engineer | 5 | 1. MR form includes: MR_ID (auto-generated), Project, Sub-project, Date, Purpose (text), Required By Date, Attachment. 2. MR_ID generated automatically in a defined format. 3. All mandatory fields validated before submission. 4. MR submitted with status 'Pending Approval'. 5. PM notified immediately on MR submission. 6. MR list view shows all submitted MRs with status badges. | UI: MR creation form with auto-ID and attachment upload. Backend: Generate MR_ID; INSERT with status = 'Pending'. DB: Material_Request(MR_ID PK, Project_ID FK, SubProject_ID FK, Date, Purpose TEXT, Required_By DATE, Status, Attachment_Path, Created_By) |
| Module IV Procurement Tracker | M4-2 | As a Project Manager, I want to approve or reject Material Requests so that only valid and justified requests proceed to procurement. | Project Manager | 3 | 1. PM sees pending MRs in an approval queue. 2. Approve or Reject buttons available per MR. 3. Rejection requires mandatory remarks. 4. Approved MR status changes to 'Approved'; rejected to 'Rejected'. 5. Site Engineer notified on approval or rejection. 6. Approval/rejection logged with PM User_ID and timestamp. | Backend: PATCH MR status; trigger notification to SE. DB: MR.Status ENUM('Pending','Approved','Rejected'), Actioned_By FK, Actioned_On, Remarks TEXT. |
| Module IV Procurement Tracker | M4-3 | As a Purchase Manager, I want to initiate RFQ so that vendor quotations can be collected for approved material requests. | Purchase Manager | 3 | 1. 'RFQ Sent' status button available on approved MRs. 2. PM selects vendors to send RFQ to from vendor master. 3. RFQ document attached optionally. 4. MR status updated to 'RFQ Sent'. 5. Vendors notified via email with RFQ details. 6. RFQ sent date recorded. | Backend: Update MR workflow state to 'RFQ Sent'; trigger email to selected vendors. DB: RFQ(RFQ_ID PK, MR_ID FK, Vendor_IDs, Sent_Date, Attachment_Path) Email: SMTP/SendGrid for vendor notification. |
| Module IV Procurement Tracker | M4-4 | As a Purchase Manager, I want to record received vendor quotations so that a vendor comparison can be performed. | Purchase Manager | 5 | 1. Quotation entry table with columns: Vendor Name, Unit Price, Lead Time, Validity, Terms. 2. Multiple vendor quotations can be entered for each MR. 3. Attachments (vendor quotes as PDFs) uploadable per entry. 4. All quotations saved under the corresponding MR. 5. Status updated to 'Quotations Received'. 6. Quotation validity dates tracked for expiry. | UI: Multi-row quotation entry table with attachment per row. Backend: INSERT quotations linked to MR_ID. DB: Quotations(Quote_ID PK, MR_ID FK, Vendor_ID, Unit_Price, Lead_Time_Days, Validity_Date, Attachment_Path) |
| Module IV Procurement Tracker | M4-5 | As a Purchase Manager, I want to perform techno-commercial comparison so that the best vendor is selected transparently. | Purchase Manager | 5 | 1. Comparison table shows all vendors side-by-side: Price, Lead Time, Terms, Technical Compliance. 2. Recommended vendor highlighted based on lowest price + compliance. 3. Manual override available to select a different vendor with justification. 4. Comparison data saved for audit purposes. 5. Selected vendor and justification locked after PM approval. | UI: Side-by-side comparison grid with highlight on recommended vendor. Backend: Store comparison results; selected vendor flagged. DB: Vendor_Comparison(Comp_ID PK, MR_ID FK, Recommended_Vendor_ID, Selected_Vendor_ID, Justification, Created_By) |
| Module IV Procurement Tracker | M4-6 | As a Purchase Manager, I want to track negotiation stages so that pricing decisions are documented and auditable. | Purchase Manager | 3 | 1. Negotiation notes section available per MR after vendor comparison. 2. Notes include: Vendor, Negotiated Price, Terms agreed, Date of negotiation. 3. Multiple negotiation rounds can be logged. 4. Final agreed price saved and compared with initial quote. 5. Price reduction % calculated and displayed. | UI: Negotiation log with expandable entries per round. Backend: INSERT negotiation rounds; compute delta from initial quote. DB: Negotiation_Log(Log_ID PK, MR_ID FK, Vendor_ID, Round INT, Price DECIMAL, Notes TEXT, Logged_By, Logged_On) |
| Module IV Procurement Tracker | M4-7 | As a Purchase Manager, I want to upload the Purchase Order so that procurement is formally documented. | Purchase Manager | 3 | 1. PO upload form includes: PO Number, Vendor, Amount, Date, File attachment. 2. PO linked to MR_ID. 3. PO upload updates MR status to 'PO Issued'. 4. Site Engineer and Project Manager notified on PO upload. 5. PO downloadable by authorized users. | UI: PO upload form with file upload. Backend: Save file; INSERT PO metadata; update MR status. DB: Purchase_Order(PO_ID PK, MR_ID FK, PO_Number, Vendor_ID, Amount, PO_Date, File_Path, Created_By) |
| Module IV Procurement Tracker | M4-8 | As a Purchase Manager, I want to track payment stages so that financial progress against the PO is monitored. | Purchase Manager | 5 | 1. Payment tracking form allows multiple payment entries per PO. 2. Fields per payment: Amount, Date, Payment Stage (Advance/Partial/Final), Reference. 3. Cumulative payment percentage bar shown (e.g., 60% paid). 4. Over-payment validation — total payments cannot exceed PO value. 5. Finance team notified on each payment entry. | UI: Payment entry table with progress bar. Backend: SUM(Payment amounts) validated against PO total. DB: Payments(Payment_ID PK, PO_ID FK, Amount DECIMAL, Stage ENUM, Date, Reference, Created_By) |
| Module IV Procurement Tracker | M4-9 | As a System, I want to track document compliance so that all required documents are validated before material delivery. | System | 5 | 1. Pre-delivery checklist shown for each PO: Test Certificates, Inspection Reports, Packing List, Invoice. 2. Each checklist item has: Status (Pending/Received), Attachment. 3. Delivery blocked until mandatory documents are marked as received. 4. Compliance % indicator shown on PO. 5. Missing documents generate alerts. | UI: Checklist UI per PO with status toggles and attachment upload. Backend: Validate mandatory items before allowing delivery status update. DB: PO_Document_Compliance(PO_ID FK, Doc_Type, Status, Attachment_Path) |
| Module IV Procurement Tracker | M4-10 | As a Purchase Manager, I want to track custom clearance status so that imported materials are monitored through the clearance process. | Purchase Manager | 3 | 1. Custom clearance status field available for POs with imported materials. 2. Status options: Not Applicable / Initiated / In Progress / Cleared. 3. Clearance date and reference number fields available. 4. Relevant stakeholders notified on status change. 5. Delays in clearance reflected in procurement timeline. | Backend: Update PO clearance status; trigger notification. DB: Purchase_Order.Clearance_Status ENUM, Clearance_Date DATE, Clearance_Ref VARCHAR |
| Module IV Procurement Tracker | M4-11 | As a System, I want to track material in transit so that delivery status is visible to the site team. | System | 3 | 1. Transit tracker shows: Dispatch Date, Expected Arrival Date, Current Status. 2. Status options: Dispatched / In Transit / Reached Site. 3. Dispatch document (GRN/Lorry Receipt) attachable. 4. Site Engineer notified when status changes to 'Reached Site'. 5. Timeline displayed as a visual tracker (stepper). | UI: Horizontal stepper showing transit stages. Backend: Update transit status; trigger site notification. DB: Material_Transit(Transit_ID PK, PO_ID FK, Dispatch_Date, Expected_Arrival, Status, Document_Path) |
| Module IV Procurement Tracker | M4-12 | As a Site Engineer, I want to record material delivery so that inventory is updated and receipt is confirmed. | Site Engineer | 5 | 1. Delivery entry form includes: Quantity Received, Date, Condition (Good/Damaged/Partial), Remarks. 2. Quantity received validated against PO quantity. 3. Partial delivery allowed — remaining quantity shown. 4. Delivery confirmation updates inventory stock level automatically. 5. Over-delivery triggers an alert for PM review. 6. Delivery document (GRN) auto-generated. | UI: Delivery form with quantity, condition, and remarks. Backend: INSERT delivery record; trigger inventory update API. DB: Material_Delivery(Delivery_ID PK, PO_ID FK, Qty_Received, Date, Condition ENUM, Remarks, Created_By) |
| Module IV Procurement Tracker | M4-13 | As a Manager, I want a procurement dashboard so that all MRs and their statuses can be monitored from a single view. | Manager | 5 | 1. Dashboard table shows all MRs with columns: MR_ID, Project, Status, Age (days), PM, Amount. 2. Status filter available: Pending / Approved / RFQ Sent / PO Issued / Delivered. 3. KPI cards: Total MRs, Pending Approvals, Delayed Deliveries. 4. Bar chart showing MR count by status. 5. Drill-down to MR detail page. 6. Exportable as Excel. | UI: Table with filters + KPI cards + status bar chart. Backend: Aggregation APIs for each widget. DB: Aggregate MR data with JOIN to Projects; indexed on Status, Created_On. |
| Module IV Procurement Tracker | M4-14 | As a System, I want notifications at each procurement stage so that users are informed of required actions. | System | 3 | 1. Notifications triggered at: MR Submission, MR Approval/Rejection, RFQ Sent, PO Issued, Material Dispatched, Material Delivered. 2. In-app + email notifications. 3. Notification includes: event type, MR/PO number, project name, action required. 4. Users can configure notification preferences. 5. Notification history retained for 90 days. | Backend: Event-driven triggers on procurement stage transitions; notification service publishes events. DB: Notifications(Notif_ID, User_ID, Event_Type, MR_ID/PO_ID, Message, Is_Read, Created_On) |
| Module IV Procurement Tracker | M4-15 | As a System, I want SLA tracking so that delays in the procurement process are highlighted and escalated. | System | 5 | 1. SLA defined per procurement stage: e.g., MR Approval ≤ 2 days, RFQ to PO ≤ 7 days. 2. SLA timer starts when stage begins. 3. Red alert indicators shown when SLA breached. 4. Escalation notification sent to manager on SLA breach. 5. SLA compliance % shown on procurement dashboard. | Backend: SLA timer computed as DATEDIFF(NOW(), Stage_Start_Date); compare against defined SLA days. DB: Procurement_SLA(Stage, Max_Days); SLA_Breach_Log(MR_ID, Stage, Breach_Date) UI: Red flag indicators in MR list and dashboard. |
| Module V Inventory Management | M5-1 | As a Store Manager, I want to create material master data so that all materials are standardized and consistently named across projects. | Store Manager | 5 | 1. Form fields: Material Code (auto/manual), Category (Civil/Mechanical/Electrical), Name, Specification, Unit of Measure, Attachments. 2. Material Code must be unique — duplicate rejected with error. 3. Category and Unit from predefined dropdown lists. 4. Specification is a free-text field for technical details. 5. Attachment supported for spec sheets. 6. Material saved to master library accessible across all projects. | UI: Clean material master creation form with dropdowns. Backend: Unique constraint check before insert. DB: Materials(Material_ID PK, Code VARCHAR UNIQUE, Category ENUM, Name, Specification TEXT, Unit, Attachment_Path) |
| Module V Inventory Management | M5-2 | As a System, I want to auto-generate material codes so that duplication is avoided and materials are uniquely identifiable. | System | 3 | 1. Material Code auto-populated when form is opened. 2. Format: Category prefix + sequential number (e.g., CIV001, MEC042). 3. Unique constraint enforced at DB level. 4. Manual code entry allowed — uniqueness still validated. 5. Code reserved upon form open to avoid race conditions. | Backend: Sequence generator per category prefix; code reserved on form load. DB: UNIQUE constraint on Materials.Code; Sequence table per category. |
| Module V Inventory Management | M5-3 | As a Store Manager, I want to create a Material Receipt Note so that all incoming stock is formally recorded. | Store Manager | 5 | 1. MRN form includes: Date, Material (searchable dropdown), Quantity, Cost, Currency, Supplier Reference, Attachment. 2. Quantity and Cost must be positive numbers. 3. MRN submission inserts stock record AND updates current inventory level. 4. MRN_ID auto-generated. 5. Store Manager and PM notified on MRN creation. 6. MRN linked to corresponding PO if applicable. | UI: MRN creation form with material search and currency dropdown. Backend: INSERT MRN + UPDATE Inventory(Current_Stock += Qty) in a single transaction. DB: MRN(MRN_ID PK, Material_ID FK, Qty, Cost DECIMAL, Currency, Date, PO_ID FK optional, Created_By) |
| Module V Inventory Management | M5-4 | As a System, I want to maintain real-time stock levels so that inventory is always accurate and up to date. | System | 5 | 1. Stock level updated in real time on every transaction (MRN, Issue, Return, Transfer). 2. Dashboard table shows: Material, Site, Current Stock, Unit, Last Updated. 3. Negative stock not allowed — validation error on issue if stock insufficient. 4. Stock history maintained for audit (all transactions logged). 5. Refresh triggered automatically on any stock-affecting event. | Backend: Inventory table updated via triggers or service calls on each stock movement. DB: Inventory(Inv_ID PK, Material_ID FK, Site_ID FK, Current_Stock DECIMAL, Last_Updated) Transaction log: Stock_Movements(Movement_ID, Material_ID, Type, Qty_Change, Balance_After, Timestamp) |
| Module V Inventory Management | M5-5 | As a System, I want to trigger reorder alerts so that stock shortages are avoided proactively. | System | 3 | 1. Each material has a configurable Minimum Threshold (reorder level). 2. When Current_Stock drops below or equals Min_Threshold, alert triggered. 3. Red indicator shown on inventory dashboard for below-threshold items. 4. Store Manager and PM receive in-app + email notification. 5. Alert not re-triggered until stock is replenished above threshold. 6. Min_Threshold configurable per material per site. | Backend: Stock comparison job: IF Current_Stock <= Min_Threshold, INSERT alert. DB: Materials.Min_Threshold DECIMAL; Inventory_Alerts(Material_ID, Site_ID, Triggered_On, Is_Resolved) UI: Red badge in inventory list. |
| Module V Inventory Management | M5-6 | As a Store Manager, I want to issue material to subcontractors so that usage is tracked and inventory is accurately reduced. | Store Manager | 5 | 1. Issue form includes: Material, Quantity, Subcontractor (dropdown), Task Reference, Date, Remarks. 2. System validates: Issue Quantity ≤ Current Stock. Error shown if insufficient stock. 3. On issuance, stock level decremented immediately. 4. Issue record linked to Task_ID for consumption tracking. 5. Subcontractor acknowledgment (sign-off) supported via digital confirmation. 6. Material Issue Slip auto-generated. | UI: Issue form with stock check indicator. Backend: Stock check before insert; deduct from Inventory in same transaction. DB: Material_Issue(Issue_ID PK, Material_ID FK, Subcontractor_ID FK, Task_ID FK, Qty, Date, Remarks, Created_By) |
| Module V Inventory Management | M5-7 | As a System, I want to track material consumption so that actual usage is compared against planned quantity for each task. | System | 5 | 1. Comparison dashboard shows Planned Qty vs Actual Consumed Qty per material per task. 2. Variance (Actual - Planned) calculated and displayed. 3. Over-consumption (>10% above plan) highlighted in amber. 4. Data source: Planned qty from task BOQ; Actual from Material_Issue. 5. Report filterable by task, material, and date range. | Backend: JOIN Task_BOQ (planned) with Material_Issue (actual) on Task_ID + Material_ID. DB: Task_BOQ(Task_ID, Material_ID, Planned_Qty); Material_Issue for actuals. UI: Comparison table with variance column and color coding. |
| Module V Inventory Management | M5-8 | As a Store Manager, I want to record material returns so that unused or surplus materials are added back to inventory. | Store Manager | 3 | 1. Return form includes: Material, Quantity Returned, Condition (Good/Damaged), Subcontractor, Reason, Date. 2. Returned quantity added back to Current_Stock. 3. Damaged materials NOT added to usable stock — logged separately. 4. Return record linked to original Issue_ID. 5. Subcontractor acknowledgment required. | Backend: INSERT return record; UPDATE Inventory WHERE Condition = 'Good'. DB: Material_Return(Return_ID PK, Issue_ID FK, Material_ID FK, Qty, Condition ENUM, Reason TEXT, Date, Created_By) |
| Module V Inventory Management | M5-9 | As a Store Manager, I want to initiate site-to-site material transfer so that materials can be redistributed between sites efficiently. | Store Manager | 5 | 1. Transfer form includes: Source Site, Destination Site, Material, Quantity, Date, Remarks, Photo. 2. Photo upload is mandatory before transfer submission. 3. System validates: Transfer Qty ≤ Source Site Stock. 4. Source site stock decremented; destination site stock incremented — both in a single DB transaction. 5. Both site managers notified on transfer. 6. Transfer record linkable to receiving MRN at destination. | Backend: Atomic transaction: Deduct from Source Inventory + Add to Destination Inventory. DB: Material_Transfer(Transfer_ID PK, Source_Site_ID FK, Dest_Site_ID FK, Material_ID FK, Qty, Photo_Path, Date, Created_By) |
| Module V Inventory Management | M5-10 | As a System, I want to enforce photo upload for material transfers so that physical movement is verified. | System | 2 | 1. Photo attachment field is mandatory on the transfer form. 2. Form submit button remains disabled until at least one photo is uploaded. 3. Supported formats: JPG, PNG. Maximum size: 10 MB per photo. 4. Up to 5 photos allowed per transfer. 5. Photos stored with transfer record and viewable in transfer detail. | Backend: Validate attachment count > 0 before INSERT. DB: Transfer_Photos(Photo_ID PK, Transfer_ID FK, File_Path, Uploaded_On) UI: Mandatory upload zone with preview thumbnails; submit button disabled until upload. |
| Module V Inventory Management | M5-11 | As a System, I want to automatically adjust stock levels after a material transfer so that inventory accuracy is maintained. | System | 3 | 1. Source site stock decremented by transfer quantity. 2. Destination site stock incremented by the same quantity. 3. Both updates occur within a single database transaction — either both succeed or both roll back. 4. Inventory balance history updated. 5. Alert triggered if source site stock drops below minimum threshold after transfer. | Backend: Database transaction wrapping two UPDATE statements. DB: UPDATE Inventory SET Current_Stock = Current_Stock - qty WHERE Site = Source; UPDATE Inventory SET Current_Stock = Current_Stock + qty WHERE Site = Destination. Rollback on failure. |
| Module V Inventory Management | M5-12 | As a Store Manager, I want to perform a stock audit so that physical stock discrepancies are identified and corrected. | Store Manager | 5 | 1. Audit form shows all materials with: System (Digital) Stock and field for Physical Count. 2. Variance = Digital - Physical automatically calculated per material. 3. Audit results saved with date and auditor name. 4. Positive and negative variances highlighted separately. 5. Adjustment entry required with reason to reconcile discrepancies. 6. Audit report exportable. | UI: Audit grid with inline physical count input and auto-calculated variance. Backend: INSERT audit record; compute variance. DB: Inventory_Audit(Audit_ID PK, Material_ID FK, Site_ID FK, Digital_Stock, Physical_Stock, Variance, Audited_By, Audit_Date) |
| Module V Inventory Management | M5-13 | As a System, I want to calculate stock variance during audits so that discrepancies are clearly visible to the audit team. | System | 2 | 1. Variance = Digital Stock - Physical Count per material. 2. Positive variance (more in system): potential theft or data entry error — flagged amber. 3. Negative variance (less in system): unrecorded issuance — flagged red. 4. Zero variance shown in green. 5. Total audit variance summary shown. | Backend: Variance = Digital_Stock - Physical_Stock; computed on audit save. DB: Stored in Inventory_Audit.Variance; indexed for audit report queries. UI: Color-coded variance cells. |
| Module V Inventory Management | M5-14 | As a Manager, I want an inventory dashboard so that stock levels across all sites are visible in one place. | Manager | 5 | 1. Dashboard table shows all materials across sites: Material, Site, Current Stock, Min Threshold, Status. 2. Site filter and category filter available. 3. Status column: Safe (above threshold) / Low (near threshold) / Critical (below threshold). 4. Color-coded status indicators. 5. Drill-down to material transaction history. 6. Exportable as Excel. | UI: Table with site and category filters + status color coding. Backend: JOIN Inventory with Materials; compute status vs Min_Threshold. DB: Aggregation query with status computation per row. |
| Module V Inventory Management | M5-15 | As a Manager, I want a stock status report so that reorder decisions can be made proactively. | Manager | 3 | 1. Report lists all materials with: Current Stock, Min Threshold, Status (Safe/Low/Critical). 2. Sortable by status — Critical items at top. 3. Reorder suggestion column shows estimated days of stock remaining. 4. Filter by site, category, status. 5. Exportable as Excel/PDF. | UI: Sortable report table with status badges. Backend: Compute Days_Remaining = Current_Stock / Avg_Daily_Consumption. DB: Aggregation on Inventory + Stock_Movements for consumption rate. |
| Module V Inventory Management | M5-16 | As a Manager, I want material consumption reports so that usage trends are visible and future planning is improved. | Manager | 3 | 1. Consumption report shows total material issued per task per time period. 2. Trend line chart showing weekly/monthly consumption. 3. Comparison: Planned Qty vs Actual Consumed. 4. Filter by project, task, material, date range. 5. Exportable as Excel. | Backend: Aggregation on Material_Issue GROUP BY Material_ID, Week/Month. DB: JOIN with Task_BOQ for planned vs actual comparison. UI: Line/bar chart with filter panel. |
| Module V Inventory Management | M5-17 | As a System, I want to support multiple currencies so that global projects with foreign-sourced materials are handled accurately. | System | 3 | 1. Currency dropdown on MRN form (USD, EUR, GBP, AED, INR, etc.). 2. Exchange rate configurable by admin. 3. Material costs stored in original currency and converted to base currency. 4. Reports show amounts in both original and base currency. 5. Currency conversion rate log maintained. | DB: MRN.Currency VARCHAR; MRN.Amount_Original DECIMAL; Currency_Rates(Currency, Rate, Effective_Date). Backend: Amount_Base = Amount_Original × Exchange_Rate. UI: Currency selector dropdown. |
| Module V Inventory Management | M5-18 | As a User, I want to attach documents to material records so that specifications and approvals are centrally available. | All Users | 2 | 1. Attachment upload section on material master form. 2. Supported formats: PDF, DOCX, JPG, PNG. 3. Multiple attachments allowed per material. 4. Attachments viewable from material detail page. 5. Download available for authorized users. | UI: Attachment upload zone on material form. Backend: Store file; INSERT metadata. DB: Material_Attachments(Attachment_ID PK, Material_ID FK, File_Path, Uploaded_By, Uploaded_On) |
| Module V Inventory Management | M5-19 | As a System, I want to support bulk material upload via Excel so that initial master data setup is completed quickly. | System | 5 | 1. Excel template downloadable from the system. 2. Uploaded Excel validated for required columns and data types. 3. Valid rows inserted as material master records. 4. Invalid rows shown in error report with row number and issue. 5. Success + error count summary displayed post-import. | Backend: Excel parser + schema validation + bulk INSERT. DB: Material master INSERT with duplicate code check. UI: Upload button + preview grid + error table. |
| Module V Inventory Management | M5-20 | As a Manager, I want an inventory value report so that the financial impact of current stock is visible. | Manager | 3 | 1. Report shows: Material, Current Stock, Unit Cost, Total Value (Stock × Cost). 2. Totals summarized by category and site. 3. Filter by site, category, date. 4. Exportable as Excel/PDF. 5. Displayed in base currency with original currency reference. | Backend: Total_Value = Current_Stock × Unit_Cost per material. DB: JOIN Inventory with MRN for latest unit cost. UI: Grouped report with category subtotals. |
| Module VI Resource Management | M6-1 | As an Admin, I want to create resources so that they can be assigned to projects and tasks for planning and tracking. | Admin | 3 | 1. Resource creation form includes: Name, Type (Work/Material/Cost), Max Units (per day), Calendar Assignment. 2. Type must be selected from predefined list. 3. Max Units defines the maximum availability per day (e.g., 8 hours for a person). 4. Resource linked to a working calendar. 5. Resource saved to a global resource pool accessible across projects. | UI: Resource creation form with type dropdown and calendar assignment. Backend: INSERT into Resources; link to Calendar. DB: Resources(Resource_ID PK, Name, Type ENUM('Work','Material','Cost'), Max_Units DECIMAL, Calendar_ID FK) |
| Module VI Resource Management | M6-2 | As a System, I want to categorize resources so that classification is maintained and reporting is structured. | System | 2 | 1. Resource types: Work (human resources), Material (physical materials), Cost (monetary resources). 2. Type displayed as a badge on resource records. 3. Resources filterable by type in all views. 4. Type-specific fields shown dynamically on form (e.g., cost resources show rate fields). | Backend: ENUM type stored; type-specific logic applied in backend services. DB: Resources.Type ENUM('Work','Material','Cost'). UI: Dynamic form fields based on selected type. |
| Module VI Resource Management | M6-3 | As a Project Manager, I want to assign resources to tasks so that work allocation and availability are managed. | Project Manager | 5 | 1. Multi-select resource picker available on task detail form. 2. Only resources within the project's resource pool shown. 3. Assignment includes: Resource, Units (%), Duration. 4. Over-allocation warning shown when assigned units exceed Max_Units. 5. Resource assignment visible on Gantt chart as resource labels. 6. Assignment logged with assigning user and timestamp. | UI: Resource picker with availability indicator; Gantt resource labels. Backend: INSERT resource assignment; validate against Max_Units. DB: Resource_Assignment(Assignment_ID PK, Task_ID FK, Resource_ID FK, Units_Percent DECIMAL, Created_By) |
| Module VI Resource Management | M6-4 | As a System, I want to track resource utilization so that efficiency is measured and workload is balanced. | System | 5 | 1. Utilization % calculated per resource: (Assigned Hours / Max Available Hours) × 100. 2. Graph view shows utilization trend over time. 3. Under-utilized resources (< 50%) highlighted in yellow. 4. Over-utilized resources (> 100%) highlighted in red. 5. Filter by project, date range, resource type. | Backend: Utilization = SUM(Assigned_Hours) / (Max_Units × Working_Days) × 100. UI: Line/area chart with utilization bands. DB: Computed from Resource_Assignment joined with working calendar. |
| Module VI Resource Management | M6-5 | As a System, I want to detect resource conflicts so that over-allocation is identified and resolved before execution. | System | 5 | 1. System checks: SUM(Assigned Units per resource per day) vs Max_Units. 2. Conflict alert shown when a resource is over-allocated for any period. 3. Conflict visible on Gantt chart (resource row highlighted red). 4. Conflict list report available with: Resource, Date, Over-allocation amount. 5. PM notified of conflicts on scheduling. | Backend: Conflict detection algorithm: aggregate daily assignments per resource. DB: JOIN Resource_Assignment with Task dates to compute daily load. UI: Red highlight on Gantt resource rows + conflict report. |
| Module VI Resource Management | M6-6 | As a User, I want to manage resource calendars so that availability, working hours, and holidays are defined. | All Users | 3 | 1. Calendar UI shows working days, non-working days, and holidays. 2. Standard calendar (Mon–Fri, 8 hrs) provided as default. 3. Custom working hours configurable per resource. 4. Holidays added per calendar. 5. Multiple calendars supported (e.g., UAE, India calendar). 6. Calendar assigned to resource at creation or later. | UI: Calendar component with day/week view; holiday management panel. Backend: Calendar rules applied during scheduling and utilization calculations. DB: Calendars(Cal_ID PK, Name); Calendar_Exceptions(Cal_ID FK, Date, Type ENUM('Holiday','NonWorking')) |
| Module VI Resource Management | M6-7 | As a System, I want to track actual resource usage so that planned vs actual comparison is available. | System | 5 | 1. Actual usage captured from task progress updates and timesheets. 2. Comparison dashboard: Planned Hours vs Actual Hours per resource. 3. Variance (over/under usage) highlighted. 4. Date range filter available. 5. Report exportable. | Backend: Compare Resource_Assignment (planned) vs Timesheet/Task_Progress (actual). DB: Timesheets(Resource_ID, Task_ID, Date, Actual_Hours) or derived from Task_Progress. UI: Comparison bar chart per resource. |
| Module VI Resource Management | M6-8 | As a Manager, I want workload charts so that resource distribution across tasks and projects is visible. | Manager | 3 | 1. Stacked bar chart shows workload per resource across multiple tasks/projects. 2. Each bar segment colored by project. 3. Max Units line overlaid on chart. 4. Filter by resource type, project, date. 5. Hover tooltip shows task details per bar segment. | UI: Stacked bar chart (Chart.js or D3) with project color coding. Backend: Aggregate Resource_Assignment per resource per period. DB: JOIN Resource_Assignment with Tasks and Projects. |
| Module VI Resource Management | M6-9 | As a Manager, I want resource reports so that allocation efficiency is monitored and future staffing is planned. | Manager | 3 | 1. Report shows: Resource Name, Type, Total Assigned Days, Utilization %, Current Tasks. 2. Filter by resource type, project, date range. 3. Highlight over- and under-utilized resources. 4. Exportable as Excel/PDF. | Backend: Aggregation on Resource_Assignment; compute utilization. DB: GROUP BY Resource_ID; JOIN with Resource master for names and type. UI: Report table with export button. |
| Module VI Resource Management | M6-10 | As a System, I want to support bulk resource import via Excel so that initial setup is completed quickly. | System | 3 | 1. Excel template downloadable from the system. 2. Uploaded file validated for required columns (Name, Type, Max Units). 3. Valid rows inserted as resource records. 4. Duplicate names flagged in error report. 5. Success + error count shown post-import. | Backend: Excel parser + schema validation + bulk INSERT. DB: Unique constraint on Resource Name within a project pool. UI: Upload form + error grid. |
| Module VII Budget Management | M7-1 | As a Project Manager, I want to create a budget using WBS structure so that cost planning is organized, hierarchical, and trackable. | Project Manager | 8 | 1. WBS hierarchy selection via drill-down dropdown (Category > Sub-category > Line item). 2. Budget amount entered per WBS line item (numeric, non-negative). 3. Budget entries can be saved in draft before final approval. 4. Budget locked after approval — no edits without admin override. 5. Budget total auto-calculated as sum of all line items. 6. Duplicate WBS line items within the same project not allowed. | UI: Hierarchical WBS selector + budget amount grid. Backend: Map budget entries to WBS; validate amounts; lock on approval. DB: Budget(Budget_ID PK, Project_ID FK, WBS_ID FK, Category, SubCategory, Amount DECIMAL, Status ENUM('Draft','Approved'), Created_By) |
| Module VII Budget Management | M7-2 | As a Project Manager, I want to define budget categories so that cost allocation is structured across all standard cost heads. | Project Manager | 3 | 1. Predefined budget categories: Material, Labour, Equipment, Subcontract, Overhead, Contingency. 2. Each category has expandable sub-categories. 3. Custom sub-categories configurable by admin. 4. Category/sub-category labels consistent across all projects. 5. Categories displayed as grouped rows in budget form. | UI: Category dropdown with sub-category expansion. Backend: Budget_Category master table with predefined values. DB: Budget_Category(Category_ID PK, Name, Parent_ID FK for sub-categories) |
| Module VII Budget Management | M7-3 | As a System, I want to lock approved budgets so that unauthorized changes are prevented and financial integrity is maintained. | System | 3 | 1. Budget transitions to 'Locked' state after PM approval. 2. All budget fields become read-only after lock. 3. Lock icon displayed on locked budget entries. 4. Any modification attempt returns validation error. 5. Admin override available with justification note and audit log entry. 6. Unlock action logged with approver and reason. | Backend: Is_Locked boolean flag; API update endpoint validates flag before allowing changes. DB: Budget.Is_Locked BOOLEAN DEFAULT FALSE; Budget_Lock_Log(Budget_ID, Locked_By, Locked_On, Reason) |
| Module VII Budget Management | M7-4 | As a User, I want to attach supporting documents to budget entries so that budget commitments are traceable and auditable. | All Users | 2 | 1. File upload section on each budget line item. 2. Supported formats: PDF, DOCX, XLSX. 3. Documents include: BOQ, PO, Work Orders, Quotations. 4. File stored in document management system with budget reference. 5. Attached documents viewable from budget line detail. | UI: File upload on budget line form. Backend: Store file; INSERT metadata with Budget_ID reference. DB: Budget_Documents(Doc_ID PK, Budget_ID FK, Doc_Type, File_Path, Uploaded_By) |
| Module VII Budget Management | M7-5 | As a User, I want to record committed amounts so that financial obligations (POs, contracts) are tracked against the approved budget. | All Users | 5 | 1. Commitment entry form: WBS reference, Committed Amount, Document Type (PO/Contract), Document Reference, Date. 2. Commitments reduce Available Budget: Available = Approved - Committed - Actual. 3. Multiple commitments allowed per WBS line. 4. Over-commitment generates warning alert. 5. Commitment locked once paid — cannot be deleted. | UI: Commitment entry form linked to WBS. Backend: Compute Available = Budget.Amount - SUM(Commitments) - SUM(Expenses). DB: Committed_Amount(Commit_ID PK, Budget_ID FK, WBS_ID FK, Amount, Doc_Type, Doc_Ref, Date, Created_By) |
| Module VII Budget Management | M7-6 | As a System, I want to track cumulative committed amounts so that budget utilization is visible at WBS and project levels. | System | 3 | 1. Cumulative committed amount computed as SUM(commitments) per WBS ID. 2. Commitment % shown: Committed / Budget × 100. 3. Progress bar per WBS line showing: Committed + Actual vs Budget. 4. Drill-down from WBS total to individual commitment entries. | Backend: SUM(Committed_Amount.Amount) GROUP BY WBS_ID. DB: Aggregation query; no separate table needed. UI: Progress bar component per WBS row. |
| Module VII Budget Management | M7-7 | As a User, I want to record actual expenses so that real cost tracking is maintained against the approved budget. | All Users | 5 | 1. Expense entry form: WBS reference, Amount, Date, Document Type, Invoice Number, Attachment. 2. Expense linked to a commitment (optional — direct expense also allowed). 3. Expense reduces Available Budget immediately on save. 4. Invoice attachment mandatory for expenses above configurable threshold. 5. Expense approval workflow for amounts above defined threshold. | UI: Expense form with WBS and commitment linkage. Backend: INSERT expense; compute updated available budget. DB: Expenses(Expense_ID PK, Budget_ID FK, WBS_ID FK, Commit_ID FK optional, Amount, Invoice_No, Attachment_Path, Created_By) |
| Module VII Budget Management | M7-8 | As a System, I want to auto-calculate remaining budget so that overspending is visible in real time. | System | 3 | 1. Remaining Budget = Approved Budget - Committed Amount - Actual Expenses. 2. Computed in real time and shown on budget dashboard. 3. Negative remaining budget (overspend) displayed in red with alert. 4. Remaining budget shown per WBS line and as project total. 5. Historical remaining budget trend chart available. | Backend: Remaining = Budget.Amount - SUM(Committed) - SUM(Expenses) computed on demand or cached. DB: No separate storage needed — derived query. UI: Inline calculation displayed on budget line rows. |
| Module VII Budget Management | M7-9 | As a Manager, I want a budget dashboard so that the overall financial status of all projects is visible at a glance. | Manager | 5 | 1. Dashboard shows: Budget vs Committed vs Actual vs Remaining per project. 2. Bar chart for budget utilization by category. 3. KPI cards: Total Budget, Total Committed, Total Spent, Remaining %. 4. Project filter and date range filter available. 5. Drill-down from dashboard to WBS-level detail. | UI: Multi-series bar chart + KPI card widgets. Backend: Aggregation APIs per widget. DB: SUM budgets, commitments, expenses per project/category. |
| Module VII Budget Management | M7-10 | As a System, I want budget threshold alerts so that project managers are notified before overspending occurs. | System | 3 | 1. Alert threshold configurable per project (e.g., 80%, 90%, 100% of budget). 2. Alert triggered when cumulative spend (committed + actual) crosses threshold. 3. Red alert indicator on budget dashboard. 4. Email + in-app notification sent to PM and Finance team. 5. Alert not re-triggered until next threshold crossed. | Backend: Threshold check job on every expense/commitment INSERT. DB: Budget_Alerts(Budget_ID, Threshold_Pct, Triggered_At, Is_Acknowledged). UI: Red indicator on budget rows and dashboard. |
| Module VIII Risk Management | M8-1 | As a Project Manager, I want to create and register risks so that potential project issues are identified early and managed proactively. | Project Manager | 5 | 1. Risk registration form includes: Title, Description, Severity (Low/Medium/High/Critical), Impact Area (Cost/Time/Quality/Safety), Probability, Attachments. 2. Risk_ID auto-generated. 3. Risk created in 'Draft' status. 4. Form validates all mandatory fields. 5. All project stakeholders notified on risk creation. 6. Risk visible in Risk Register. | UI: Risk creation form with severity dropdown and impact area multi-select. Backend: INSERT risk; trigger notification. DB: Risk(Risk_ID PK, Project_ID FK, Title, Description TEXT, Severity ENUM, Impact_Area, Probability, Status, Created_By) |
| Module VIII Risk Management | M8-2 | As a User, I want to define severity levels for risks so that risks can be prioritized effectively. | All Users | 2 | 1. Severity options: Low, Medium, High, Critical. 2. Color coding: Green (Low), Yellow (Medium), Orange (High), Red (Critical). 3. Severity affects risk scoring (Severity × Probability). 4. Risks sortable by severity in risk register. 5. Dashboard filters by severity level. | Backend: Severity ENUM stored; Risk_Score = Severity_Value × Probability. DB: Severity defined as ENUM in Risk table. UI: Color-coded badges per severity. |
| Module VIII Risk Management | M8-3 | As a User, I want to assign stakeholders to risks so that responsibility for monitoring and mitigation is clearly defined. | All Users | 3 | 1. Multi-select user dropdown on risk form for stakeholder assignment. 2. Each risk has: Risk Owner (1 person) and Stakeholders (multiple). 3. Risk Owner is responsible for mitigation updates. 4. All assigned stakeholders notified on risk status changes. 5. Stakeholder list editable by PM. | UI: Multi-select user picker for stakeholders; single-select for Risk Owner. Backend: INSERT stakeholder assignments. DB: Risk_Stakeholders(Risk_ID FK, User_ID FK, Role ENUM('Owner','Stakeholder')) |
| Module VIII Risk Management | M8-4 | As a Reviewer, I want to approve or reject risks so that only validated risks proceed to the mitigation and analysis stage. | Reviewer / Manager | 3 | 1. Reviewer sees pending risks in 'Draft' status for review. 2. Approve or Reject action with mandatory remarks. 3. Approved risks move to 'Under Analysis' status. 4. Rejected risks returned to creator with rejection reason. 5. Approval logged with reviewer ID and timestamp. | Backend: PATCH risk status with role validation; notify creator on reject. DB: Risk.Status ENUM('Draft','Under Analysis','Mitigation','Closed','Rejected'), Reviewed_By, Reviewed_On, Review_Remarks |
| Module VIII Risk Management | M8-5 | As a Planning Engineer, I want to analyze risks so that mitigation strategies, timelines, and contingency plans are documented. | Planning Engineer | 5 | 1. Risk analysis form includes: Root Cause Analysis, Mitigation Plan, Contingency Plan, Target Resolution Date. 2. Risk matrix displayed showing Probability vs Impact visual. 3. Analysis saved and risk status updated to 'Mitigation'. 4. Analysis document attachable. 5. Risk score recalculated after analysis. | UI: Analysis form with risk matrix visualization. Backend: INSERT analysis data; update risk status. DB: Risk_Analysis(Analysis_ID PK, Risk_ID FK, Root_Cause, Mitigation_Plan TEXT, Contingency_Plan TEXT, Target_Date, Created_By) |
| Module VIII Risk Management | M8-6 | As a Manager, I want to assign a Risk Owner so that accountability for each risk is clearly defined. | Manager | 2 | 1. Risk Owner dropdown available on risk detail page. 2. Filtered to active project team members. 3. Risk Owner receives notification on assignment. 4. Risk Owner responsible for submitting mitigation progress updates. 5. Owner displayed on risk register list. | Backend: UPDATE Risk SET Owner_ID = ?; trigger notification. DB: Risk.Owner_ID INT FK REFERENCES Users(User_ID) |
| Module VIII Risk Management | M8-7 | As a Risk Owner, I want to update mitigation progress so that the effectiveness of the risk response is tracked. | Risk Owner | 3 | 1. Mitigation update form includes: Progress Notes, % Mitigation Complete, Attachment, Date. 2. Multiple update entries allowed (chronological log). 3. When % Complete = 100, risk can be moved to 'Closed'. 4. All stakeholders notified on each update. 5. Progress log viewable from risk detail page. | UI: Update form with progress notes and attachment. Backend: INSERT mitigation update; notify stakeholders. DB: Risk_Mitigation_Log(Log_ID PK, Risk_ID FK, Notes TEXT, Percent_Complete INT, Attachment_Path, Updated_By, Updated_On) |
| Module VIII Risk Management | M8-8 | As a System, I want to track the risk lifecycle so that status transitions are maintained and risks are not left unresolved. | System | 3 | 1. Risk lifecycle: Draft → Review → Under Analysis → Mitigation → Closed. 2. Status stepper displayed on risk detail page. 3. Transitions follow defined rules — no skipping stages. 4. Each transition logged with user and timestamp. 5. Closed risks archived but remain searchable. | Backend: State machine enforcing valid transitions per role. DB: Risk.Status ENUM + Risk_Status_Log(Risk_ID, From_Status, To_Status, Changed_By, Changed_On) |
| Module VIII Risk Management | M8-9 | As a Manager, I want a risk dashboard so that risk distribution across severity and status is visible. | Manager | 3 | 1. Pie chart showing risk count by severity (Low/Medium/High/Critical). 2. Bar chart showing risks by status (Draft/Analysis/Mitigation/Closed). 3. Risk matrix heatmap (Probability vs Severity). 4. KPI cards: Total Open Risks, Critical Risks, Overdue Mitigations. 5. Filter by project and date range. 6. Drill-down to risk register. | UI: Pie, bar, and heatmap charts using Chart.js. Backend: Aggregation queries per chart. DB: GROUP BY Severity, Status on Risk table. |
| Module VIII Risk Management | M8-10 | As a System, I want high severity risks to automatically appear in the DPR so that management is always aware of critical threats. | System | 3 | 1. DPR generation includes a 'High/Critical Risks' section. 2. Risks with Severity = 'High' or 'Critical' and Status != 'Closed' auto-pulled into DPR. 3. Risk section in DPR shows: Risk ID, Title, Severity, Owner, Mitigation Status. 4. Risks cleared from DPR only when status = 'Closed'. 5. DPR risk section configurable (can be toggled on/off by admin). | Backend: DPR generation API queries Risk WHERE Severity IN ('High','Critical') AND Status != 'Closed'. Integration: Risk module exposes endpoint consumed by DPR service. DB: JOIN Risk with Risk_Stakeholders for owner info. |
| DPR Daily Progress Report | DPR-1 | As a System, I want to generate the DPR automatically at a scheduled time so that daily reporting is consistent and no manual effort is required. | System | 8 | 1. DPR generation job runs at 11:00 AM daily (configurable). 2. Data pulled from: Task Progress, Labour, Equipment, Material Consumption, Risk, Weather. 3. Draft DPR created and sent to Site Engineer for review. 4. If no data available for a module, that section shows 'No data recorded'. 5. DPR generation failure triggers an alert to admin. 6. Each DPR versioned by date and project. | Backend: Scheduled job (CRON/Celery) at 11 AM. Pulls data from all relevant modules. DB: DPR(DPR_ID PK, Project_ID FK, Date, Status ENUM('Draft','Submitted','Approved'), Generated_At) |
| DPR Daily Progress Report | DPR-2 | As a Manager, I want the DPR to include work progress data so that daily execution status is clearly visible. | Manager | 5 | 1. DPR Work Progress section shows all tasks updated on that day. 2. For each task: Task Name, % Complete, Planned vs Actual, Remarks. 3. Summary: Total tasks active, Total tasks completed today. 4. Tasks with no update shown as 'No Update Recorded'. 5. Progress data sourced from Task_Progress table for the report date. | Backend: Query Task_Progress WHERE Date = DPR_Date; JOIN with Tasks for names and planned data. DB: JOIN Task_Progress with Tasks, Projects for full context. DPR Section: Work_Progress[] |
| DPR Daily Progress Report | DPR-3 | As a Manager, I want the DPR to include delay details so that risks to project schedule are highlighted every day. | Manager | 3 | 1. DPR Delays section lists all delays logged on the report date. 2. Columns: Task Name, Delay Type, Hours Lost, Description. 3. Total delay hours summarized. 4. Delays categorized by type (Weather/Labour/Material/Equipment/Client). 5. Sourced from Task_Delay table. | Backend: Query Task_Delay WHERE Logged_On = DPR_Date. DB: JOIN Task_Delay with Tasks for task names. DPR Section: Delay_Summary[] |
| DPR Daily Progress Report | DPR-4 | As a Manager, I want the DPR to include manpower deployment so that daily workforce visibility is ensured. | Manager | 3 | 1. DPR Labour section shows trade-wise planned vs actual headcount. 2. Table: Trade ¦ Planned ¦ Actual ¦ Variance. 3. Total manpower count summarized. 4. Sourced from Labour_Attendance table for the report date. 5. Data shown only for approved entries. | Backend: Query Labour_Attendance WHERE Date = DPR_Date AND Status = 'Approved'. DB: GROUP BY Trade; JOIN with Tasks for task context. DPR Section: Labour_Summary[] |
| DPR Daily Progress Report | DPR-5 | As a Manager, I want the DPR to include equipment usage so that resource tracking is complete in the daily report. | Manager | 3 | 1. DPR Equipment section shows: Equipment Name, Type, Hours Used, Status (Working/Breakdown). 2. Total equipment hours summarized. 3. Equipment on breakdown flagged in red. 4. Sourced from Resource module (equipment type resources). 5. Data for report date only. | Backend: Query Resource_Assignments WHERE Resource.Type = 'Equipment' AND Date = DPR_Date. DB: JOIN Resources with Resource_Assignment and task dates. DPR Section: Equipment_Summary[] |
| DPR Daily Progress Report | DPR-6 | As a Manager, I want the DPR to include material consumption so that daily inventory usage is tracked and documented. | Manager | 3 | 1. DPR Material section shows: Material Name, Quantity Used, Unit, Task Reference. 2. Total material value consumed (if cost data available). 3. Sourced from Material_Issue table for the report date. 4. Linked to tasks for context. | Backend: Query Material_Issue WHERE Date = DPR_Date. DB: JOIN with Materials for names, Tasks for context. DPR Section: Material_Consumption[] |
| DPR Daily Progress Report | DPR-7 | As a User, I want to export the DPR as a PDF so that it can be easily shared with stakeholders and kept as a record. | All Users | 3 | 1. 'Export PDF' button available on DPR detail page. 2. PDF matches the predefined DPR template format (company letterhead, sections in order). 3. PDF includes: Project Name, Date, All Sections (Progress, Labour, Equipment, Material, Delays, Risks). 4. Generated PDF downloadable immediately. 5. PDF stored in Document Management system with project reference. | Backend: PDF generation using a library (e.g., WeasyPrint, Puppeteer, JasperReports). DB: DPR_PDF_Log(DPR_ID, File_Path, Generated_By, Generated_On) UI: Export button with download trigger. |
| DPR Daily Progress Report | DPR-8 | As a System, I want the DPR to follow a predefined template format so that consistency is maintained across all projects and dates. | System | 3 | 1. DPR sections always appear in fixed order: Work Progress → Delays → Labour → Equipment → Material → Risks → Weather. 2. Section headings, table columns, and layout match the approved DPR template. 3. Company logo and project details in header. 4. Page numbers in footer. 5. Template configurable by admin (section toggling, logo upload). | Backend: DPR template engine with configurable sections. DB: DPR_Template_Config(Section_Name, Is_Enabled, Display_Order) per project/global. UI: Admin panel for template configuration. |
| MVH Excel Integration | MVH-1 | As a Planning Engineer, I want to upload an MVH Excel file so that tasks can be bulk-created quickly without manual data entry. | Planning Engineer | 5 | 1. Upload button on Task page accepting .xlsx and .xls formats. 2. File size limit: 25 MB. 3. Preview grid shown after upload with first 20 rows visible. 4. Editable cells in preview for minor corrections. 5. 'Import' button visible only after preview is validated. 6. Imported tasks linked to the current project. | UI: Upload + preview grid with editable cells. Backend: Parse Excel using xlsx/openpyxl; display parsed rows in preview. DB: Staging table for preview data; final insert on user confirmation. |
| MVH Excel Integration | MVH-2 | As a System, I want to validate the Excel format before import so that incorrectly structured files are rejected with clear error messages. | System | 5 | 1. Required columns validated: Task Name, Start Date, End Date, Duration, Parent Task. 2. Data types checked: dates must be valid dates, duration must be numeric. 3. Row-level validation errors shown in error grid: Row #, Column, Error Description. 4. File with missing mandatory columns rejected entirely with header-level error. 5. Validation runs before any data is inserted. | Backend: Column header check + row-level data type validation before insert. DB: Validation_Error_Log(Import_Session_ID, Row_Number, Column, Error) UI: Error grid rendered post-upload. |
| MVH Excel Integration | MVH-3 | As a System, I want to map Excel columns to database fields so that data is stored correctly regardless of column naming variations. | System | 5 | 1. Column mapping configuration defines: Excel Column Name → DB Field. 2. Mapping configurable by admin to handle different Excel templates. 3. Unmapped required columns trigger a mapping error before import. 4. Optional columns mapped if present; ignored if absent. 5. Mapping rules saved per template type. | Backend: Mapping config table used during parse; transform Excel column to DB field. DB: Column_Mapping(Template_Type, Excel_Column, DB_Field, Is_Required) UI: Admin mapping configuration panel. |
| MVH Excel Integration | MVH-4 | As a System, I want to handle bulk inserts efficiently so that large Excel files are imported without performance degradation. | System | 5 | 1. Valid rows inserted using batch INSERT statements (not row-by-row). 2. Batch size configurable (default: 500 rows per batch). 3. Import progress bar shown for files > 100 rows. 4. Transaction wraps all batch inserts — rollback if any batch fails. 5. Import completion time < 30 seconds for 1000 rows. | Backend: Batch INSERT using prepared statements; chunked by batch size. DB: Bulk INSERT within DB transaction; rollback on error. Performance: Target < 30s for 1000 rows on standard DB hardware. |
| MVH Excel Integration | MVH-5 | As a User, I want an error report after Excel import so that I can identify and correct invalid rows before re-uploading. | All Users | 3 | 1. Error report displayed immediately after import validation. 2. Report shows: Row Number, Column with Error, Error Description. 3. Valid row count and error row count summary shown. 4. Error report downloadable as Excel. 5. User can fix errors in original file and re-upload. 6. Partial import option: import valid rows, skip invalid. | UI: Error grid with row-level details + summary counts + download button. Backend: Return error list in API response; optional partial import flag. DB: Import_Session(Session_ID, Total_Rows, Valid_Rows, Error_Rows, Created_By, Created_On) |
| MVH Excel Integration | MVH-6 | As a System, I want to rollback the entire import on failure so that data integrity is maintained and partial imports are avoided. | System | 3 | 1. All inserts for an import session wrapped in a single database transaction. 2. If any insert fails mid-import, all previous inserts in that session are rolled back. 3. Error message shown to user explaining rollback occurred. 4. Failed import logged with session details and error cause. 5. Data state identical to before the import attempt. | Backend: DB transaction wrapping all batch INSERTs; ROLLBACK on exception. DB: ACID-compliant transaction; Import_Session logged with status 'Failed' on rollback. UI: Error notification with rollback confirmation message. |